Project Preparation Advance
for Modernization of Government Services Project

Project ID No. P148537

Reference No.: 02/1.1/IC

TERMS OF REFERENCE

International Consultant to provide support for re-engineering 
of three selected public services

- Background

Country background

The Government of Moldova is determined to fundamentally change the way how public services are provided in Moldova through a variety of interventions for modernization of service delivery, which combat corruption, foster a customer care culture, enhance access, as well as increases efficiency in the Moldovan public administration.

Therefore, one of the main objectives of the Administration Reform Strategy 2016-2020 and Government’s working program for years 2016-2018 is the modernization of public services.

Moldova has made considerable progress both in terms of public administration reform, exceeding indicators average of countries in Europe and Central Asia and countries with middle and low income, as well as the size of Government modernization that uses information and communication technology (ICT), the Government of creating a world-class ICT infrastructure that allows the development and supply of electronic services to the highest quality standards.

Current situation in the sector

Even though some progress has been made over the last decade, citizens still view corruption as a significant problem. While business process and e-governance reform efforts have somewhat improved business services, such measures have not yet been applied to administrative services.

Businesses and citizens continue to face many constraints in the interaction with the state, one of the most important of which is corruption perceived by 40 percent of companies as a major impediment to business (according to the World Bank, EBRD Business Environment and Enterprise Performance Survey (2013). Institutional reforms aimed at reducing corruption are also at the forefront of the EU’s requirements for Moldova’s progress.  The most important challenges ahead are strengthening the rule of law, reforms in public administration, including professionalism and anti-corruption efforts and improving competitiveness and the business environment.

Although the Government has launched the reform of public services in 2014-2016 and has committed to digitize and provide online access to all public services by 2020, lack of capacity and expertise to perform re-engineering and process optimization remains a problem that prevents achieving this.

Also, there is room for rationalization to over 580 existing public services by withdrawing from use the obsolete services.

To meet these challenges, the Government, in accordance with the Public Administration Reform Strategy for the years 2016-2020 (especially the component "Modernization of Public Services") plans a major transformation exercise (qualitative and quantitative) of administrative public services, provided by central public administration authorities through: a) removing outdated public services or merging several services in one; b) increasing access to local public services through various channels; c) reducing the number of documents required for public services, and the time needed for delivery; e) ensuring a high level of satisfaction with the quality of government service delivery.

The Government of Moldova has requested the assistance of the World Bank for a PAR operation, planned for 2017 - 2021 (Modernization of Government Services Project – MGSP). Major results of the operation include better quality, accessibility, and increased efficiency of selected governmental administrative services through the following components:

- Administrative Service Modernization

The key activities under this component focus on re-engineering a group of government to citizen and government to business administrative services, piloting of one-stop-shops for public service delivery in selected locations and explore the possibility of rolling out at national level; increased awareness of citizens on public services and availability of e-services.

- Digital Platform and Services

The main objective of this component is to digitize selected re-engineered government services; complete and strengthen a common infrastructure and mechanisms for rapid deployment of ICT-enabled public services; introduce government wide IT Management and Cyber Security standards and procedures. It will finance the acquisition of additional shared computing infrastructure elements, digitization of services needed to deliver Government services electronically and development of IT Management and Cyber Security standards and procedures as well as learning management system to mainstream them within the government.

- Implementation of a Service Delivery Model

The objective of this Component is to ensure that the institutional capabilities of key government agencies are aligned with and support the new model of public services delivery. Technical assistance will be provided to all institutions responsible for the delivery of public services re-engineered and digitized under MGSP, as well as partner entities participating in Unified Public Services centers (CUPS) pilots. The Component will also address the capabilities of structural units in the government responsible for public services modernization reform management and coordination.

Under MGSP, the Government undertakes a multilayered reform that focuses on key administrative central government public services to reduce time and burden for citizens and businesses and improve service delivery quality, transparency and efficiency by using innovative solutions and ICT. Its key pillars are: i) modernization of the public services so that they are more accessible to any citizen and business; ii) service provision standardization, simplification through business process re-engineering and digitization, with a focus on on-line services; iii) citizen feedback and performance monitoring on service delivery for on-going improvement.

An Individual Consultant will be hired to assist the e-Government Center with bidding evaluation and providing consultancy on conducting re-engineering of 3 (three) selected public services.

- Objective of the assignment

The main goal of the assignment is to assist the e-Government Center’s team to ensure a thorough, transparent and impartial evaluation of the proposals submitted by Consulting Firms for re-engineering of 3 public services and perform quality assurance of project deliverables.

# Scope of Work

## Task 1. Evaluation of proposals for re-engineering of three selected services

Analyze relevant project documentation, including Project appraisal document (PAD), Methodology for re-engineering of public services, Action plan for public services modernization reform 2017-2021, Terms of reference for re-engineering of three selected public services etc., to get a better understanding of the public services modernization reform;

Assist the evaluation committee in evaluation of Expressions of Interest received from Consulting Firms based on the shortlisting criteria included in the approved TORs and prepare a technical note for the evaluation committee;

Assist eGC’s Procurement Specialist to prepare the technical evaluation report in the required format;

## Task 2. Support in contract drafting and negotiation

- Review and provide inputs to the draft contract included in the Request for Proposals (RFP);

- Assist eGC in negotiating the Contract;

## Task 3. Assist eGC team in managing the re-engineering of three selected services

Validate, together with relevant eGC team members the project implementation plan;

Assist eGC team with tackling project issues and risks as well as support eGC’s Change Management activities in beneficiary institutions to ensure proper buy-in and support of the re-engineering process;

Assist eGC team in getting approval and sign-off of the ‘to-be’ maps and implementation plan by the relevant stakeholders;

## Task 4. Perform quality control of re-engineering deliverables

Review the “as is” and “to be” maps of each service and recommendations for administrative streamlining and improving the service delivery;

Provide inputs to proposed service standard charts and implementation action plan;

- Outputs

## Task 1. Evaluation

Technical evaluation note.

## Task 2. Review draft contract

- Recommendations to the draft contract with the Consulting Firms included in the Request for Proposals (RFP).

## Task 3. Assist eGC team in managing the re-engineering team

Proposals to the project implementation plan submitted by the re-engineering team;

Recommendations to improve the re-engineering process of the three selected services based on Consultant’s observations of the re-engineering process.

## Task 4. Perform quality control of re-engineering deliverables

Review report of the “as is” and “to be” maps of each service and the recommendations for administrative streamlining and improving the service delivery;

Recommendations on proposed service standard charts and implementation action plan.

- Timing

- The assignment is expected to start in August 2017. The estimated duration of the assignment is 9 months with an estimated level of effort of 20 days.

- Institutional arrangements

The Consultant will report to the Executive Director of the e-Government Center and work under the direct supervision of designated eGC project manager.

- Resources

- The Consultant is expected to work from his/her office. Up to two short-term trips to Moldova are anticipated, to allow the Consultant to offer support for project launch as well as validation/sign-off of the deliverables together with the beneficiary institutions. The Consultant should also be available for consultations and meetings via VC/phone calls.

- Qualification requirements and evaluation criteria

- Master Degree in law or business management or any other relevant area for the project;

- Ten (10) years of professional experience in institutional development and/or change management experience is required out of which preferably 5 (five), but not less than 3 (three) years of professional experience in regulatory reform;

- Experience as team leader in at least 3 (three) projects of comparable size concerning organizational change/set up of public sector institutions in an EU Member State, candidate and/or potential candidate country;

- Fluency in English, both written and spoken (min 2 points in the scale from 1 to 5 where 1 is excellent and 5 is basic);

- Computer literate.