Modernization of Government Services

- in the Republic of Moldova Project

# Project ID No. P148537
TERMS OF REFERENCE
INDIVIDUAL CONSULTANT TO DEVELOP THE CHANGE MANAGEMENT FRAMEWORK

# BACKGROUND

From 2006 to 2013, Moldova modernized its civil service legislation and administrative processes under the Central Public Administration Reform (CPAR), supported by the World Bank administered CPAR MDTF. However, additional efforts are needed to transform Moldova public administration and bring it closer to the EU standards as planned under the Action Plan for implementation of the Association Agreement with the EU, signed in 2014.

Governance is identified as a cross-cutting issue and interventions are planned to improve the business enabling environment, enhance public administration reform and quality of public service delivery. The Government has requested the World Bank assistance for a PAR operation, planned for delivery commencing in FY18 to 2023, called Modernization of Government Services Project (MGSP, the Project).

MGSP design takes into account the Government of Moldova vision, stated in the Public Administration Reform Strategy 2016-2020, relies on the Government Services Modernization Action Plan for 2017-2021 and makes extensive use of institutional and technological achievements of Governance e-Transformation Project (GeT) implemented by the Government of Moldova and World Bank in the past years. The project will aim to achieve improvements in access, efficiency and quality of delivery of selected administrative services through the following four components:

1.	Public Service Modernization

The key activities under this component focus on re-engineering a group of government to citizen and government to business administrative services, piloting of one-stop-shops for public service delivery in selected locations and explore the possibility of rolling out at national level; increased awareness of citizens on public services and availability of e-services.

2.	Digital Platform and Services

The main objective of this component is to digitize selected re-engineered government services; complete and strengthen a common infrastructure and mechanisms for rapid deployment of ICT-enabled public services; introduce government wide IT Management and Cyber Security standards and procedures. It will finance the acquisition of additional shared computing infrastructure elements, digitization of services needed to deliver Government services electronically and development of IT Management and Cyber Security standards and procedures as well as learning management system to mainstream them within the government.

3.	Aligning institutional capabilities to new model of service delivery

The objective of this Component is to ensure that the institutional capabilities of key government agencies are aligned with and support the new model of public services delivery.

Current situation in the area:

The GeT Project implementation process demonstrated that line ministries’ and other Government Agencies’ buy-in is essential for an efficient Business Processes Review and services digitization. It is well known that changes in business processes often require adjustments in organizational structure, working methods, and changes in organizational culture, with a greater focus on performance and the needs of service users. All this requires a significant commitment for change of line ministries management at all levels, as well as clear directions and guidelines for an efficient management of the necessary institutional and functional changes to minimize the adverse effects of service reengineering and digitization on service employees and ensure the smooth transition from the current situation to a more efficient and effective service delivery model.

In the recent years, public sector organizations have been demanded to ensure increased efficiency and effectiveness. These organizations are expected to develop new relationships and partnerships, think and act strategically, network with other agencies, manage resources effectively, redefine boundaries of systems, and govern for accountability and transparency. The rise of these expectations has created challenges and the need for change, including the way public servants operate in their daily activity. In these instances, governments increasingly rely on change management practices, which are a solution for organizations to adapt to external or internal shifts.

Under the same Component 3, technical assistance will be provided to all institutions responsible for the delivery of public services re-engineered and digitized under MGSP, as well as partner entities participating in Centres for Unified Public Services (CUPS) pilots. The Component will also address the capabilities of structural units in the government responsible for public services modernization reform management and coordination. Specifically, Component 3 of the MGSP will support the adjustment of institutional and staff capacities of key Government agencies to the new citizen-centric model and digital administrative service delivery arrangements. Component 3 - valid for all line ministries and agencies responsible for the selected Government services under MGSP - is foreseen to be managed and coordinated by the State Chancellery Public Administration Directorate (PA Directorate) responsible for human resources policy coordination and management of public services.

4.	Project Management

This Component will finance project implementation unit (PIU), based in e-Governance Agency and will co-finance the core e-Governance Agency management team.

# OBJECTIVE

The objective of the assignment is the development of a systematic, structured and integrated framework to manage the institutional and functional changes of public service providers and to support capacity development of the relevant managerial staff to implement the change management framework in the process of institutional redesign and/or transition to new service delivery models.

# SCOPE OF WORK

The consultant is expected to perform the following tasks to achieve the objective:

- Develop a work plan to be applied for the respective assignment with details on the implementation of the main activities/tasks of the assignment, their duration and interrelations, milestones (including interim approvals by the Client), and tentative delivery dates of the deliverables/reports;

- Analyze the MGSP components relevant to the assignment as well as the draft Methodology on Government administrative services reengineering and propose entry points for putting their implementation in more holistic citizen centric context;

- Undertake a comprehensive desk review of the key documents and existing information related to public administration reform in general and citizen-centric modernization of Government administrative services in particular;

- Explore and share existing best practices and models (e.g. Lewin, ADKAR, Kotter, Covey, Kubbler-Ross) related to organizational change management, and identify the ones which are relevant to the public sector context of the Republic of Moldova.

- Develop a comprehensive change management framework that will explain the main steps and activities to be realized to ensure a good management of the institutional and functional changes within the institutions that are subject to reform and reengineering processes;

The framework should take into consideration the unique characteristics and needs of the public sector and the way transformational change should be carried out in these organizations, and focus, among other aspects, on:

- specifications of processes to be followed to operate change;

- leadership aspects related to encouraging and supporting change; and

- delegation aspects related to empowering others to encourage and operate change.

The document shall also emphasize the collaborative nature of change and the need to involve all parts of the organization to diagnose the organization’s bottlenecks and jointly develop solutions for specific changes to address these issues. Such a collaborative approach shall aim to foster grassroots change which, is generally, more sustainable.

Also, the document shall focus on understanding, recognizing and managing resistance to change as well as on communication aspects that are required for a successful transformation.

Finally, the change management framework shall look into incorporating organizational culture into organizational change as the former emerged as pivotal in determining the success of leaders' efforts to implement change initiatives.

- Develop the training curricula and training materials on change management, that will provide the necessary theoretical information and practical solutions for the senior and middle managerial staff to be used during the transition period from the current to the new model of delivery of reengineered Government administrative services;

- Deliver a series of training activities for the relevant staff of public institutions responsible for the management and coordination of change agenda towards the new model of Government administrative service delivery;

- Perform training evaluations and present the quantitative and qualitative data related to the delivered trainings, lessons learned and potential adjustments of training materials and delivery models, as well as recommendations for further activities related to the capacity development process in the change management field;

- Prepare and present the Final Report on the assignment with details on the activities performed, relevant mission findings and recommendations, list of deliverables and delivery dates.

- DELIVERABLES AND TIMEFRAME

The deliverables under this assignment are as specified in the table below. All documents submitted must be aligned to the following minimum standards:

- Use appropriate language for a non-technical audience

- Be comprehensive, properly formatted and well presented

- Provide justifications for all assumptions

- Show evidence of consultation.

| No. | Deliverables | Tentative timeframe/deadline |
| --- | --- | --- |
| 1 | A detailed Workplan to be applied for the respective assignment developed | In two weeks from the contracting date |
| 2 | First draft of the Change management framework developed and presented to the beneficiary for review and comments The change management framework should include but not be limited to: - General overview of the approach to be applied when dealing with the necessary institutional and functional changes in the institution; - Description of the current policies, regulations and procedures related to the handling with the functional as well as staff matters arising out of organizational change in the public sector; - Mechanisms and structures to be established within the entities to enable organizational change initiatives; - A change management toolkit, including templates for transition plan, outlining all the necessary steps and activities to be realized in the process; - Relevant tools for communication, engagement and encouragement of the people to get buy-in towards the new model of service delivery etc.; - Necessary tools enabling managers to manage and lead change initiatives. | In one month from the acceptance of the Workplan |
| 3 | Revised draft of the Change management framework presented | In two weeks from the receipt of the comments and proposals of the beneficiary |
| 3 | Training curricula and training materials for the course on change management developed | In 3 weeks from the acceptance by the beneficiary of the deliverable 3 |
| 4 | Two full day training activities* for the relevant staff of public institutions responsible for the management and coordination of change agenda organized | To be decided |
| 5 | Training Evaluation Report developed | In two weeks from the last training delivered |
| 6 | Final Report on the assignment with relevant mission findings and recommendations developed, details on the activities performed, list of deliverables and delivery dates | In one week from the acceptance of the deliverable 5. |

* The exact dates of trainings will be decided in consultation with the beneficiary

# TIMING

This is a part-time assignment expected to be performed during the period April-July 2019.

The work will be performed both on-site in Chisinau and also off-site at the consultant’s premises. The Consultant should be available for consultations and meetings via VC/phone calls upon request by the State Chancellery or EGA.

# INSTITUTIONAL ARRANGEMENTS

The Consultant will work under the direct supervision of the State Chancellery Public Administration Directorate in association with the Inter Component Coordinator and MGSP Project Manager ensuring qualitative and timely implementation of the envisaged tasks and submission of expected deliverables.

# QUALIFICATION REQUIREMENTS AND EVALUATION CRITERIA

Mandatory qualifications

- University degree or higher degree in public administration, political science, social sciences or other related to the assignment disciplines;

- Minimum 8 years of extensive work experience on public administration reform and human resources management fields;

- Minimum 5 years in developing training materials and delivery of trainings in the fields of public administration reform, institutional change and human resources management;

- Certified specialized trainings in Change management and/or Human resources management;

- Experience in developing and implementing change management strategies/policies within public organizations;

- Very strong interpersonal and communication skills;

- Proven analytical, organizational, reporting and writing abilities (the candidates shall provide details on documents developed under different assignments, also mentioning their role in such exercises, i.e. author, co-author, member of the developing team, etc. The Client can request additional information on the mentioned document during the evaluation process);

- Ability to effectively communicate and write in English language.

Preferred qualifications

- Experience in working with teams on multi-disciplinary analytical work and similar assignments conducted by the World Bank, IMF, UNO and other donors financed projects;

- Good knowledge of the Moldova case and the local context;

- Previous experience in the implementation of activities related to the Government Service Modernization Agenda;

- Knowledge of Romanian and/or Russian languages.